## Read First
Introduction
This PERT analysis Template is made by Yasir Masood - PMP using Excel. He is mechanical and
mechatronics engineer. Also certified PMP from PMI USA.
Expert in Project Planning, Project Risk Management, Project Management and solutions for |  | DisClaimer
Engineering problems. Good command on Top notch Scheduling, planning and Risk Manage- |  | This template is made for learning and understan-
ment software as well as Monte Carlos Simulation. |  | ding the PERT concept. However Author will not be
responsible for any error, fault, loss and demage
casue by using this template.
Author has right to change its content without any
prior notice!
Note:
1- Project PERT Analysis is always conducted on project
critical path. That is the longest path in the network
diagram
2- Non-Critical Path Activities are excluded from PERT
Analysis
3- Enter 'Yes' for Critical Activities and 'No' for Non-Critical
Activities in Column 'G'
4- For Excel 2007 and Up
5- If activites are more then Use only critical path activies
for analysis.
6- Do enter Target or due days in E126!
If any one is interested in PERT Analysis using Monte Carlos Simulation (Senitivity Analysis, Percentile, Probability of achieving target date etc.) Then contact me at yasir91109@gmail.com or projects416@gmail.com.
Available for contractual and permanent assignments!
Only for Ms Excel 2007 & Above

## Project-PERT-Analysis-Extended
PROJECT PERT ANALYSIS
S.No. | Activities | Column1 | Duration (Days) |  |  | Critical Path | PERT | Activity Standard Deviation | Activity Variance
|  | Duration | Optimistic | Most Likely | Pessimistic |  |  | (P-O)/6 | {(P-O)/6}^2
1 | Activity 1 | 123.33 days |  |  |  |  | 0 | 0 | 0
2 | Activity 2 | 124.33 days |  |  |  |  | 0 | 0 | 0
3 | Activity 3 | 210.83 days |  |  |  |  | 0 | 0 | 0
4 | Activity 4 | 30 days |  |  |  |  | 0 | 0 | 0
5 | Activity 5 | 40 days |  |  |  |  | 0 | 0 | 0
6 | Activity 6 | 40.83 days |  |  |  |  | 0 | 0 | 0
7 | Activity 7 | 70 days |  |  |  |  | 0 | 0 | 0
8 | Activity 8 | 60 days |  |  |  |  | 0 | 0 | 0
9 | Activity 9 | 331.67 days |  |  |  |  | 0 | 0 | 0
10 | Activity 10 | 60 days |  |  |  |  | 0 | 0 | 0
11 | Activity 11 | 51.67 days |  |  |  |  | 0 | 0 | 0
12 | Activity 12 | 70 days |  |  |  |  | 0 | 0 | 0
13 | Activity 13 | [5 empty] | 0 | 0 | 0
14 | Activity 14 | [5 empty] | 0 | 0 | 0
15 | Activity 15 | [5 empty] | 0 | 0 | 0
16 | Activity 16 | [5 empty] | 0 | 0 | 0
17 | Activity 17 | [5 empty] | 0 | 0 | 0
18 | Activity 18 | [5 empty] | 0 | 0 | 0
19 | Activity 19 | [5 empty] | 0 | 0 | 0
20 | Activity 20 | [5 empty] | 0 | 0 | 0
21 | Activity 21 | [5 empty] | 0 | 0 | 0
22 | Activity 22 | [5 empty] | 0 | 0 | 0
23 | Activity 23 | [5 empty] | 0 | 0 | 0
24 | Activity 24 | [5 empty] | 0 | 0 | 0
25 | Activity 25 | [5 empty] | 0 | 0 | 0
26 | Activity 26 | [5 empty] | 0 | 0 | 0
27 | Activity 27 | [5 empty] | 0 | 0 | 0
28 | Activity 28 | [5 empty] | 0 | 0 | 0
29 | Activity 29 | [5 empty] | 0 | 0 | 0
30 | Activity 30 | [5 empty] | 0 | 0 | 0
31 | Activity 31 | [5 empty] | 0 | 0 | 0
32 | Activity 32 | [5 empty] | 0 | 0 | 0
33 | Activity 33 | [5 empty] | 0 | 0 | 0
34 | Activity 34 | [5 empty] | 0 | 0 | 0
35 | Activity 35 | [5 empty] | 0 | 0 | 0
36 | Activity 36 | [5 empty] | 0 | 0 | 0
37 | Activity 37 | [5 empty] | 0 | 0 | 0
38 | Activity 38 | [5 empty] | 0 | 0 | 0
39 | Activity 39 | [5 empty] | 0 | 0 | 0
40 | Activity 40 | [5 empty] | 0 | 0 | 0
41 | Activity 41 | [5 empty] | 0 | 0 | 0
42 | Activity 42 | [5 empty] | 0 | 0 | 0
43 | Activity 43 | [5 empty] | 0 | 0 | 0
44 | Activity 44 | [5 empty] | 0 | 0 | 0
45 | Activity 45 | [5 empty] | 0 | 0 | 0
46 | Activity 46 | [5 empty] | 0 | 0 | 0
47 | Activity 47 | [5 empty] | 0 | 0 | 0
48 | Activity 48 | [5 empty] | 0 | 0 | 0
49 | Activity 49 | [5 empty] | 0 | 0 | 0
50 | Activity 50 | [5 empty] | 0 | 0 | 0
51 | Activity 51 | [5 empty] | 0 | 0 | 0
52 | Activity 52 | [5 empty] | 0 | 0 | 0
53 | Activity 53 | [5 empty] | 0 | 0 | 0
54 | Activity 54 | [5 empty] | 0 | 0 | 0
55 | Activity 55 | [5 empty] | 0 | 0 | 0
56 | Activity 56 | 50 days |  |  |  |  | 0 | 0 | 0
57 | Activity 57 | 71.67 days |  |  |  |  | 0 | 0 | 0
58 | Activity 58 | 71.67 days |  |  |  |  | 0 | 0 | 0
59 | Activity 59 | 53.33 days |  |  |  |  | 0 | 0 | 0
60 | Activity 60 | 40 days |  |  |  |  | 0 | 0 | 0
61 | Activity 61 | 130 days |  |  |  |  | 0 | 0 | 0
62 | Activity 62 | 644.17 days |  |  |  |  | 0 | 0 | 0
63 | Activity 63 | 188 days |  |  |  |  | 0 | 0 | 0
64 | Activity 64 | 257.5 days |  |  |  |  | 0 | 0 | 0
65 | Activity 65 | 577.67 days |  |  |  |  | 0 | 0 | 0
66 | Activity 66 | 320.67 days |  |  |  |  | 0 | 0 | 0
67 | Activity 67 | 1763 days? |  |  |  |  | 0 | 0 | 0
68 | Activity 68 | 67.17 days |  |  |  |  | 0 | 0 | 0
69 | Activity 69 | 1689.67 days? |  |  |  |  | 0 | 0 | 0
70 | Activity 70 | 387 days |  |  |  |  | 0 | 0 | 0
71 | Activity 71 | 207 days |  |  |  |  | 0 | 0 | 0
72 | Activity 72 | 1362 days |  |  |  |  | 0 | 0 | 0
73 | Activity 73 | 100 days |  |  |  |  | 0 | 0 | 0
74 | Activity 74 | 140 days |  |  |  |  | 0 | 0 | 0
75 | Activity 75 | 330 days |  |  |  |  | 0 | 0 | 0
76 | Activity 76 | 110 days |  |  |  |  | 0 | 0 | 0
77 | Activity 77 | 160 days |  |  |  |  | 0 | 0 | 0
78 | Activity 78 | 136.67 days |  |  |  |  | 0 | 0 | 0
79 | Activity 79 | 80 days |  |  |  |  | 0 | 0 | 0
80 | Activity 80 | 80 days |  |  |  |  | 0 | 0 | 0
81 | Activity 81 | 51.67 days |  |  |  |  | 0 | 0 | 0
82 | Activity 82 | 50.83 days |  |  |  |  | 0 | 0 | 0
83 | Activity 83 | 120 days |  |  |  |  | 0 | 0 | 0
84 | Activity 84 | 70 days |  |  |  |  | 0 | 0 | 0
85 | Activity 85 | 130 days |  |  |  |  | 0 | 0 | 0
86 | Activity 86 | 588.33 days |  |  |  |  | 0 | 0 | 0
87 | Activity 87 | 190 days |  |  |  |  | 0 | 0 | 0
88 | Activity 88 | 488.33 days |  |  |  |  | 0 | 0 | 0
89 | Activity 89 | 1678.33 days |  |  |  |  | 0 | 0 | 0
90 | Activity 90 | 70 days |  |  |  |  | 0 | 0 | 0
91 | Activity 91 | 110 days |  |  |  |  | 0 | 0 | 0
92 | Activity 92 | 130 days |  |  |  |  | 0 | 0 | 0
93 | Activity 93 | 230 days |  |  |  |  | 0 | 0 | 0
94 | Activity 94 | 130 days |  |  |  |  | 0 | 0 | 0
95 | Activity 95 | 111.67 days |  |  |  |  | 0 | 0 | 0
96 | Activity 96 | 171.67 days |  |  |  |  | 0 | 0 | 0
97 | Activity 97 | 130 days |  |  |  |  | 0 | 0 | 0
98 | Activity 98 | 151.67 days |  |  |  |  | 0 | 0 | 0
99 | Activity 99 | 178.33 days |  |  |  |  | 0 | 0 | 0
100 | Activity 100 | 113.33 days |  |  |  |  | 0 | 0 | 0
101 | Activity 101 | 121.67 days |  |  |  |  | 0 | 0 | 0
102 | Activity 102 | 170 days |  |  |  |  | 0 | 0 | 0
103 | Activity 103 | 100 days |  |  |  |  | 0 | 0 | 0
104 | Activity 104 | 320 days |  |  |  |  | 0 | 0 | 0
105 | Activity 105 | 320 days |  |  |  |  | 0 | 0 | 0
106 | Activity 106 | 154.17 days |  |  |  |  | 0 | 0 | 0
107 | Activity 107 | 100 days |  |  |  |  | 0 | 0 | 0
108 | Activity 108 | 155 days |  |  |  |  | 0 | 0 | 0
109 | Activity 109 | 826.67 days |  |  |  |  | 0 | 0 | 0
110 | Activity 110 | 60 days |  |  |  |  | 0 | 0 | 0
Critical Path
Yes
Project PERT
| Project Duration (Days) |  | Expected Date | 0
| Project Variance |  | Ʃ {(P-O)/6}^2 | 0
| Project Standard Deviation |  | √Project Variance | 0
| Project Expeted Days |  | Calculted as Above | 0
| Project Due Days (Target Date) |  | User Value
| Standard Normal Equation |  | Z | #DIV/0!
| Probaility of Meeting Target Date (Due Date) % |  | % | Missing value
Missing value
#DIV/0!
#DIV/0!
Missing value
[10 empty] | Z | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
[10 empty] | 0 | 0.5 | 0.504 | 0.508 | 0.512 | 0.516 | 0.5199 | 0.5239 | 0.5279 | 0.5319 | 0.5359
[10 empty] | 0.1 | 0.5398 | 0.5438 | 0.5478 | 0.5517 | 0.5557 | 0.5596 | 0.5636 | 0.5675 | 0.5714 | 0.5753
[10 empty] | 0.2 | 0.5793 | 0.5832 | 0.5871 | 0.591 | 0.5948 | 0.5987 | 0.6026 | 0.6064 | 0.6103 | 0.6141
[10 empty] | 0.3 | 0.6179 | 0.6217 | 0.6255 | 0.6293 | 0.6331 | 0.6368 | 0.6406 | 0.6443 | 0.648 | 0.6517
[10 empty] | 0.4 | 0.6554 | 0.6591 | 0.6628 | 0.6664 | 0.67 | 0.6736 | 0.6772 | 0.6808 | 0.6844 | 0.6879
[10 empty] | 0.5 | 0.6915 | 0.695 | 0.6985 | 0.7019 | 0.7054 | 0.7088 | 0.7123 | 0.7157 | 0.719 | 0.7224
[10 empty] | 0.6 | 0.7257 | 0.7291 | 0.7324 | 0.7357 | 0.7389 | 0.7422 | 0.7454 | 0.7486 | 0.7517 | 0.7549
[10 empty] | 0.7 | 0.758 | 0.7611 | 0.7642 | 0.7673 | 0.7704 | 0.7734 | 0.7764 | 0.7794 | 0.7823 | 0.7852
[10 empty] | 0.8 | 0.7881 | 0.791 | 0.7939 | 0.7967 | 0.7995 | 0.8023 | 0.8051 | 0.8078 | 0.8106 | 0.8133
[10 empty] | 0.9 | 0.8159 | 0.8186 | 0.8212 | 0.8238 | 0.8264 | 0.8289 | 0.8315 | 0.834 | 0.8365 | 0.8389
[10 empty] | 1 | 0.8413 | 0.8438 | 0.8461 | 0.8485 | 0.8508 | 0.8531 | 0.8554 | 0.8577 | 0.8599 | 0.8621
[10 empty] | 1.1 | 0.8643 | 0.8665 | 0.8686 | 0.8708 | 0.8729 | 0.8749 | 0.877 | 0.879 | 0.881 | 0.883
[10 empty] | 1.2 | 0.8849 | 0.8869 | 0.8888 | 0.8907 | 0.8925 | 0.8944 | 0.8962 | 0.898 | 0.8997 | 0.9015
[10 empty] | 1.3 | 0.9032 | 0.9049 | 0.9066 | 0.9082 | 0.9099 | 0.9115 | 0.9131 | 0.9147 | 0.9162 | 0.9177
[10 empty] | 1.4 | 0.9192 | 0.9207 | 0.9222 | 0.9236 | 0.9251 | 0.9265 | 0.9279 | 0.9292 | 0.9306 | 0.9319
[10 empty] | 1.5 | 0.9332 | 0.9345 | 0.9357 | 0.937 | 0.9382 | 0.9394 | 0.9406 | 0.9418 | 0.9429 | 0.9441
[10 empty] | 1.6 | 0.9452 | 0.9463 | 0.9474 | 0.9484 | 0.9495 | 0.9505 | 0.9515 | 0.9525 | 0.9535 | 0.9545
[10 empty] | 1.7 | 0.9554 | 0.9564 | 0.9573 | 0.9582 | 0.9591 | 0.9599 | 0.9608 | 0.9616 | 0.9625 | 0.9633
[10 empty] | 1.8 | 0.9641 | 0.9649 | 0.9656 | 0.9664 | 0.9671 | 0.9678 | 0.9686 | 0.9693 | 0.9699 | 0.9706
[10 empty] | 1.9 | 0.9713 | 0.9719 | 0.9726 | 0.9732 | 0.9738 | 0.9744 | 0.975 | 0.9756 | 0.9761 | 0.9767
[10 empty] | 2 | 0.9772 | 0.9778 | 0.9783 | 0.9788 | 0.9793 | 0.9798 | 0.9803 | 0.9808 | 0.9812 | 0.9817
[10 empty] | 2.1 | 0.9821 | 0.9826 | 0.983 | 0.9834 | 0.9838 | 0.9842 | 0.9846 | 0.985 | 0.9854 | 0.9857
[10 empty] | 2.2 | 0.9861 | 0.9864 | 0.9868 | 0.9871 | 0.9875 | 0.9878 | 0.9881 | 0.9884 | 0.9887 | 0.989
[10 empty] | 2.3 | 0.9893 | 0.9896 | 0.9898 | 0.9901 | 0.9904 | 0.9906 | 0.9909 | 0.9911 | 0.9913 | 0.9916
[10 empty] | 2.4 | 0.9918 | 0.992 | 0.9922 | 0.9925 | 0.9927 | 0.9929 | 0.9931 | 0.9932 | 0.9934 | 0.9936
[10 empty] | 2.5 | 0.9938 | 0.994 | 0.9941 | 0.9943 | 0.9945 | 0.9946 | 0.9948 | 0.9949 | 0.9951 | 0.9952
[10 empty] | 2.6 | 0.9953 | 0.9955 | 0.9956 | 0.9957 | 0.9959 | 0.996 | 0.9961 | 0.9962 | 0.9963 | 0.9964
[10 empty] | 2.7 | 0.9965 | 0.9966 | 0.9967 | 0.9968 | 0.9969 | 0.997 | 0.9971 | 0.9972 | 0.9973 | 0.9974
[10 empty] | 2.8 | 0.9974 | 0.9975 | 0.9976 | 0.9977 | 0.9977 | 0.9978 | 0.9979 | 0.9979 | 0.998 | 0.9981
[10 empty] | 2.9 | 0.9981 | 0.9982 | 0.9982 | 0.9983 | 0.9984 | 0.9984 | 0.9985 | 0.9985 | 0.9986 | 0.9986
[10 empty] | 3 | 0.9987 | 0.9987 | 0.9987 | 0.9988 | 0.9988 | 0.9989 | 0.9989 | 0.9989 | 0.999 | 0.999
[10 empty] | 3.1 | 0.999 | 0.9991 | 0.9991 | 0.9991 | 0.9992 | 0.9992 | 0.9992 | 0.9992 | 0.9993 | 0.9993
[10 empty] | 3.2 | 0.9993 | 0.9993 | 0.9994 | 0.9994 | 0.9994 | 0.9994 | 0.9994 | 0.9995 | 0.9995 | 0.9995
[10 empty] | 3.3 | 0.9995 | 0.9995 | 0.9995 | 0.9996 | 0.9996 | 0.9996 | 0.9996 | 0.9996 | 0.9996 | 0.9997
[10 empty] | 3.4 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9997 | 0.9998
[10 empty] | 3.5 | 0.99977
[10 empty] | 4 | 0.99997
[10 empty] | 4.5 | 1
[10 empty] | 5 | 1
[10 empty] | -3.4 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0003 | 0.0002
[10 empty] | -3.3 | 0.0005 | 0.0005 | 0.0005 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0004 | 0.0003
[10 empty] | -3.2 | 0.0007 | 0.0007 | 0.0006 | 0.0006 | 0.0006 | 0.0006 | 0.0006 | 0.0005 | 0.0005 | 0.0005
[10 empty] | -3.1 | 0.001 | 0.0009 | 0.0009 | 0.0009 | 0.0008 | 0.0008 | 0.0008 | 0.0008 | 0.0007 | 0.0007
[10 empty] | -3 | 0.0013 | 0.0013 | 0.0013 | 0.0012 | 0.0012 | 0.0011 | 0.0011 | 0.0011 | 0.001 | 0.001
[10 empty] | -2.9 | 0.0019 | 0.0018 | 0.0018 | 0.0017 | 0.0016 | 0.0016 | 0.0015 | 0.0015 | 0.0014 | 0.0014
[10 empty] | -2.8 | 0.0026 | 0.0025 | 0.0024 | 0.0023 | 0.0023 | 0.0022 | 0.0021 | 0.0021 | 0.002 | 0.0019
[10 empty] | -2.7 | 0.0035 | 0.0034 | 0.0033 | 0.0032 | 0.0031 | 0.003 | 0.0029 | 0.0028 | 0.0027 | 0.0026
[10 empty] | -2.6 | 0.0047 | 0.0045 | 0.0044 | 0.0043 | 0.0041 | 0.004 | 0.0039 | 0.0038 | 0.0037 | 0.0036
[10 empty] | -2.5 | 0.0062 | 0.006 | 0.0059 | 0.0057 | 0.0055 | 0.0054 | 0.0052 | 0.0051 | 0.0049 | 0.0048
[10 empty] | -2.4 | 0.0082 | 0.008 | 0.0078 | 0.0075 | 0.0073 | 0.0071 | 0.0069 | 0.0068 | 0.0066 | 0.0064
[10 empty] | -2.3 | 0.0107 | 0.0104 | 0.0102 | 0.0099 | 0.0096 | 0.0094 | 0.0091 | 0.0089 | 0.0087 | 0.0084
[10 empty] | -2.2 | 0.0139 | 0.0136 | 0.0132 | 0.0129 | 0.0125 | 0.0122 | 0.0119 | 0.0116 | 0.0113 | 0.011
[10 empty] | -2.1 | 0.0179 | 0.0174 | 0.017 | 0.0166 | 0.0162 | 0.0158 | 0.0154 | 0.015 | 0.0146 | 0.0143
[10 empty] | -2 | 0.0228 | 0.0222 | 0.0217 | 0.0212 | 0.0207 | 0.0202 | 0.0197 | 0.0192 | 0.0188 | 0.0183
[10 empty] | -1.9 | 0.0287 | 0.0281 | 0.0274 | 0.0268 | 0.0262 | 0.0256 | 0.025 | 0.0244 | 0.0239 | 0.0233
[10 empty] | -1.8 | 0.0359 | 0.0351 | 0.0344 | 0.0336 | 0.0329 | 0.0322 | 0.0314 | 0.0307 | 0.0301 | 0.0294
[10 empty] | -1.7 | 0.0446 | 0.0436 | 0.0427 | 0.0418 | 0.0409 | 0.0401 | 0.0392 | 0.0384 | 0.0375 | 0.0367
[10 empty] | -1.6 | 0.0548 | 0.0537 | 0.0526 | 0.0516 | 0.0505 | 0.0495 | 0.0485 | 0.0475 | 0.0465 | 0.0455
[10 empty] | -1.5 | 0.0668 | 0.0655 | 0.0643 | 0.063 | 0.0618 | 0.0606 | 0.0594 | 0.0582 | 0.0571 | 0.0559
[10 empty] | -1.4 | 0.0808 | 0.0793 | 0.0778 | 0.0764 | 0.0749 | 0.0735 | 0.0721 | 0.0708 | 0.0694 | 0.0681
[10 empty] | -1.3 | 0.0968 | 0.0951 | 0.0934 | 0.0918 | 0.0901 | 0.0885 | 0.0869 | 0.0853 | 0.0838 | 0.0823
[10 empty] | -1.2 | 0.1151 | 0.1131 | 0.1112 | 0.1093 | 0.1075 | 0.1056 | 0.1038 | 0.102 | 0.1003 | 0.0985
[10 empty] | -1.1 | 0.1357 | 0.1335 | 0.1314 | 0.1292 | 0.1271 | 0.1251 | 0.123 | 0.121 | 0.119 | 0.117
[10 empty] | -1 | 0.1587 | 0.1562 | 0.1539 | 0.1515 | 0.1492 | 0.1469 | 0.1446 | 0.1423 | 0.1401 | 0.1379
[10 empty] | -0.9 | 0.1841 | 0.1814 | 0.1788 | 0.1762 | 0.1736 | 0.1711 | 0.1685 | 0.166 | 0.1635 | 0.1611
[10 empty] | -0.8 | 0.2119 | 0.209 | 0.2061 | 0.2033 | 0.2005 | 0.1977 | 0.1949 | 0.1922 | 0.1894 | 0.1867
[10 empty] | -0.7 | 0.242 | 0.2389 | 0.2358 | 0.2327 | 0.2296 | 0.2266 | 0.2236 | 0.2206 | 0.2177 | 0.2148
[10 empty] | -0.6 | 0.2743 | 0.2709 | 0.2676 | 0.2643 | 0.2611 | 0.2578 | 0.2546 | 0.2514 | 0.2483 | 0.2451
[10 empty] | -0.5 | 0.3085 | 0.305 | 0.3015 | 0.2981 | 0.2946 | 0.2912 | 0.2877 | 0.2843 | 0.281 | 0.2776
[10 empty] | -0.4 | 0.3446 | 0.3409 | 0.3372 | 0.3336 | 0.33 | 0.3264 | 0.3228 | 0.3192 | 0.3156 | 0.3121
[10 empty] | -0.3 | 0.3821 | 0.3783 | 0.3745 | 0.3707 | 0.3669 | 0.3632 | 0.3594 | 0.3557 | 0.352 | 0.3483
[10 empty] | -0.2 | 0.4207 | 0.4168 | 0.4129 | 0.409 | 0.4052 | 0.4013 | 0.3974 | 0.3936 | 0.3897 | 0.3859
[10 empty] | -0.1 | 0.4602 | 0.4562 | 0.4522 | 0.4483 | 0.4443 | 0.4404 | 0.4364 | 0.4325 | 0.4286 | 0.4247
[10 empty] | 0 | 0.5 | 0.496 | 0.492 | 0.488 | 0.484 | 0.4801 | 0.4761 | 0.4721 | 0.4681 | 0.4641
[10 empty] | -3.5 | 0.00023263
[10 empty] | -4 | 3.167e-05
[10 empty] | -4.5 | 3.4e-06
[10 empty] | -5 | 2.9e-07
Note on B120: Yasir Masood - PMP: Based on Critical Path. That is the longest path.
Note on D127: Engineer: =(Due date -Expected date)/Project Standard Deviation
Note on E126: Engineer: Specified the value or specified target days to complete the project.
Note on E128: Engineer: If value Comes Zero It means. It is not present in 'Normal Curve Area Table'
Note on G3: Yasir Masood -PMP: Type ' YES' If activity is on Critical path. Other wise NO.